## Old Tasks (2)
|  |  | Sprint 1 |  |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
Task | Week 1 | Week 2 | Week 3 | Week 4 | Break | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Marking Activity | Comments
Individual Tasks
Individual Retrospective | Unit Chair | Unit Chair | Supervisor | Supervisor | Break | Supervisor |  | Supervisor |  |  |  |  | To be discussed during meeting | Mandatory Task
SWOT & Project Preference | Unit Chair
Grading Agreement | Unit Chair
Spike |  | Unit Chair
Grade Milestone Report | [7 empty] | Supervisor (Graded) |  |  |  |  | Outside of Meeting | Optional Task
Learning Summary Report Draft | [9 empty] | Supervisor |  |  | Outside of Meeting | Mandatory Task
Team Tasks (one per team)
Team Worklog |  |  | Supervisor | Supervisor | Break | Supervisor | Supervisor | Supervisor | Supervisor | Supervisor | Supervisor | Supervisor | To be discussed during meeting | Mandatory Task
IP Agreement |  |  | Supervisor | [9 empty] | To be discussed during meeting | Mandatory Task
Granting Access to Supervisor and Unit Chair |  |  | Supervisor | [9 empty] | To be discussed during meeting | Mandatory Task
Draft Scope / Scope Review |  |  | Supervisor | [9 empty] | To be discussed during meeting | Week 3 Mandatory, Reviews optional if things change
Sprint Increment |  |  |  | Supervisor |  |  | Supervisor |  | Supervisor |  | Supervisor |  | To be discussed during meeting | Mandatory Task
Sprint Retrospective |  |  |  | Supervisor |  |  | Supervisor |  | Supervisor |  | Supervisor |  | To be discussed during meeting | Mandatory Task
Repository Log | [11 empty] | Supervisor | Outside of Meeting | Mandatory Task
Trello Log | [11 empty] | Supervisor | Outside of Meeting | Mandatory Task

## Old Tasks
|  |  | Sprint 1 |  |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
Task | Week 1 | Week 2 | Week 3 | Week 4 | Break | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Marking Activity | Comments
Individual Tasks
Individual Retrospective | Unit Chair | Unit Chair | Supervisor | Supervisor | Break | Supervisor | Supervisor | Supervisor | Supervisor | Supervisor | Supervisor | Supervisor | To be discussed during meeting | Mandatory Task
SWOT & Project Preference | Unit Chair
Grading Agreement | Unit Chair
Spike |  | Unit Chair | [10 empty] | To be discussed during meeting
Pass Grade Milestone | [6 empty] | Supervisor |  |  |  |  | Supervisor | Outside of Meeting | Mandatory Task
Credit Grade Milestone | [6 empty] | Supervisor |  |  |  |  | Supervisor | Outside of Meeting | Optional Task
Distinction Grade Milestone | [6 empty] | Supervisor |  |  |  |  | Supervisor | Outside of Meeting | Optional Task
High Distinction Grade Milestone | [6 empty] | Supervisor |  |  |  |  | Supervisor | Outside of Meeting | Optional Task
[7 empty] | Grade Milestone Report |  |  |  |  | Learning Summary Report Draft 2
Team Tasks (one per team)
Team Worklog |  |  | Supervisor | Supervisor | Break | Supervisor | Supervisor | Supervisor | Supervisor | Supervisor | Supervisor | Supervisor | To be discussed during meeting | Mandatory Task
IP Agreement |  |  | Supervisor | [9 empty] | To be discussed during meeting | Mandatory Task
Granting Access to Supervisor and Unit Chair |  |  | Supervisor | [9 empty] | To be discussed during meeting | Mandatory Task
Draft Scope / Scope Review |  |  | Supervisor | [9 empty] | To be discussed during meeting | Week 3 Mandatory, Reviews optional if things change
Sprint Increment |  |  |  | Supervisor |  |  | Supervisor |  | Supervisor |  | Supervisor |  | To be discussed during meeting | Mandatory Task
Sprint Retrospective |  |  |  | Supervisor |  |  | Supervisor |  | Supervisor |  | Supervisor |  | To be discussed during meeting | Mandatory Task
Repository Log | [11 empty] | Supervisor | Outside of Meeting | Mandatory Task
Trello Log | [11 empty] | Supervisor | Outside of Meeting | Mandatory Task
|  |  | Sprint 1 |  |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
Task | Week 1 | Week 2 | Week 3 | Week 4 | Break | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Marking Activity | Comments
Individual Tasks
Individual Retrospective | Unit Chair | Unit Chair | Supervisor | Supervisor | Break | Supervisor |  | Supervisor |  | Supervisor |  | Supervisor | To be discussed during meeting | Mandatory Task
SWOT & Project Preference | Unit Chair
Grading Agreement | Unit Chair
Spike |  | Unit Chair
Grade Milestone Report | [6 empty] | Supervisor (Graded) | [5 empty] | Outside of Meeting | Optional Task
Learning Summary Report Draft | [11 empty] | Supervisor | Outside of Meeting | Mandatory Task
Team Tasks (one per team)
Team Worklog |  |  | Supervisor | Supervisor | Break | Supervisor | Supervisor | Supervisor | Supervisor | Supervisor | Supervisor | Supervisor | To be discussed during meeting | Mandatory Task
IP Agreement |  |  | Supervisor | [9 empty] | To be discussed during meeting | Mandatory Task
Granting Access to Supervisor and Unit Chair |  |  | Supervisor | [9 empty] | To be discussed during meeting | Mandatory Task
Draft Scope / Scope Review |  |  | Supervisor | [9 empty] | To be discussed during meeting | Week 3 Mandatory, Reviews optional if things change
Sprint Increment |  |  |  | Supervisor |  |  | Supervisor |  | Supervisor |  | Supervisor |  | To be discussed during meeting | Mandatory Task
Sprint Retrospective |  |  |  | Supervisor |  |  | Supervisor |  | Supervisor |  | Supervisor |  | To be discussed during meeting | Mandatory Task
Repository Log | [11 empty] | Supervisor | Outside of Meeting | Mandatory Task
Trello Log | [11 empty] | Supervisor | Outside of Meeting | Mandatory Task

## New Tasks
|  |  | Sprint 1 |  |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
Task | Week 1 | Week 2 | Week 3 | Week 4 | Break | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Marking Activity | Comments
Individual Tasks
Individual Retrospective | Unit Chair | Unit Chair | Supervisor | Supervisor | Break | Supervisor |  | Supervisor |  | Supervisor |  | Supervisor | To be discussed during meeting | Mandatory Task
SWOT & Project Preference | Unit Chair
Grading Agreement | Unit Chair
Spike |  | Unit Chair
Grade Milestone Report | [6 empty] | Supervisor (Graded) | [5 empty] | Outside of Meeting | Optional Task
Learning Summary Report Draft | [11 empty] | Supervisor | Outside of Meeting | Mandatory Task
Team Tasks (one per team)
Team Worklog |  |  | Supervisor | Supervisor | Break | Supervisor | Supervisor | Supervisor | Supervisor | Supervisor | Supervisor | Supervisor | To be discussed during meeting | Mandatory Task
IP Agreement |  |  | Supervisor | [9 empty] | To be discussed during meeting | Mandatory Task
Granting Access to Supervisor and Unit Chair |  |  | Supervisor | [9 empty] | To be discussed during meeting | Mandatory Task
Draft Scope / Scope Review |  |  | Supervisor | [9 empty] | To be discussed during meeting | Week 3 Mandatory, Reviews optional if things change
Sprint Increment |  |  |  | Supervisor |  |  | Supervisor |  | Supervisor |  | Supervisor |  | To be discussed during meeting | Mandatory Task
Sprint Retrospective |  |  |  | Supervisor |  |  | Supervisor |  | Supervisor |  | Supervisor |  | To be discussed during meeting | Mandatory Task
Repository Log | [11 empty] | Supervisor | Outside of Meeting | Mandatory Task
Trello Log | [11 empty] | Supervisor | Outside of Meeting | Mandatory Task